## Slide 1
21 March 2023
VENUE: Polytechnic University, Tirana
CONFERENCE
ON THE DEVELOPMENT OF PORT INFRASTRUCTURE AND TEN-T COMPLIANCE INDICATORS
Panel 2 - STRATEGIC INVESTMENTS ON MARITIME: WHAT TO CONSIDER?
Albanian Railway Sector Experience - JASPERS example
ACTION PLAN
for capacity strengthening for the management of railway infrastructure projects

## Slide 2
PREPARATION OF THE ACTION PLAN
Supported by JASPERS, the Action Plan has been prepared by the concerned national authorities, such as:
- The Ministry of Infrastructure and Energy (MIE);
- The railway company of Albania (HSH), and
- The State Agency of Strategic Programming and Aid Coordination (SASPAC) / NIPAC;
- EIB, EBRD, EC (DG NEAR).
THE OBJECTIVE
- to demonstrate that through a set of the activities, a feasible and sustainable implementation structure will gradually be established to ensure that the project “Rehabilitation and modernization of the railway line Vora-Han i Hotit” will be constructed and put into operation in quality and timely manner;
- To ensure that the capacities established will serve even for the future important projects that will be implemented in the railway infrastructure.

## Slide 3
In the preparation of this Action Plan a particular attention was paid to the following aspects:
• Assessing what implementation capacity can reasonably be required for implementation of the project “Vora-Hani I Hotit”;
• Assessing what capacity is available and/or can be reasonably ensured by HSH, and
• Identifying the initial most feasible way to address the above aspects, considering the constraints.

## Slide 4
The most important conclusion refers to the potential support of EIB for creating the initial enabling conditions regarding remuneration of the PMIU staff during a period of maximum 5 years and the commitment of the national authorities to ensure sustainability of the PMIU structure and its integration into the future RIMA within the above-mentioned period of 5 years (from 01 January 2023).

## Slide 5
AP consist of 4 actions, which are divided in different Activities.
Action 1: Create Enabling Environment
This action and the related activities refer to pre-requisites for the overall success of the Action Plan. It is beyond the responsibilities and impact of MIE and HSH only, and requires incentives from a higher political level and from the side of the International Financing Institutions (IFIs), i.e. the EBRD and EIB as well as from the European Commission.
Action 2: Finalization of Project Preparation Activities and Initiation of Project Implementation
This action and the related activities shall be performed and accomplished irrespectively of the timing for strengthening the implementation capacity for the project implementation (particularly of the PMIU of HSH). The majority of the activities shall be performed by the PMIU of HSH with support of MIE. Considering the current structure of the PMIU of HSH, the tasks shall be assigned immediately to the “Foreign project management group in the field of design and technical assistance from foreign donors”.

## Slide 6
Action 3: Strengthening the capacity of the PMIU
- Ensure gradual improvements in the structure and capacity of the PMIU to enable smooth preparation and implementation of the projects;
- Ensure conditions for the sustainability of the structure and capacity of the PMIU.
- Contribute to restructuring of HSH and establishing a new entity to be responsible for the development and maintenance of the railway infrastructure (RIMA).
In addition, the training programmes are usually of a rolling nature, related to the following main aspects:
• The expertise and experience of the experts which are subject to the capacity building;
• Availability of competent experts / companies to perform trainings, and
• Availability of funding for capacity building / trainings.

## Slide 7
Action 4: Operation and Maintenance of new Assets (subject to separate Action Plans)
Basically, the current circumstances do not allow the development of more precise action plans for future operation and maintenance of the new assets to be acquired through various implementation project. They will depend on the outcomes of the restructuring process, clarifications and agreements between the national authorities and IFIs. Also, such Action Plans, due to their content and scope, are usually separated from Action Plans for project preparation and implementation.
It was suggested that those Action Plans are prepared along the process of the restructuring of HSH / the railway sector.
In this document are included only some main “issues/reminders” for future development of the Action Plans for Operation and Maintenance.

## Slide 8
The Albanian MIE is fully committed on the successful implementation of the AP, in order to ensure that the conditions and capacities created and strengthened during the transition period will remain following the end of the EIB’s financial support and that PMIU structure will continue to operate efficiently without losing the gained expertise.
The progress of the activities, will be reported to the EBRD, EIB and EC on a quarterly basis.
The main party responsible for the reporting is the Ministry of Infrastructure and Energy (MIE) with support of the PMIU of HSH.

## Slide 9
THANK YOU!
Zana Josa, MBA
Ministry of Infrastructure and Energy
e-mail : zana.joca@infrastruktura.gov.al